# Owner’s Permits(RTB Permits)

| Category | Permit |
| --- | --- |
| Land | Land Lease |
| Environmental | Environmental Approval (“Carta de Pertinencia” or RCA, as applicable) |
| Sectorial | Land Usage Permit (IFC “Informe Favorable para Construccion”, SAG resolution) |
|  | Land Usage Permit (IFC “Informe Favorable para Construccion”, MINVU resolution) |
|  | Industrial rating (“Calificación industrial”, SEREMI resolution). If this permit is pending on Signing Date of the EPC Agreement it shall be the responsability of the Contractor to obatin it at Contractor´s sole expense. |
| Building Permits | Preliminary Works Permit, if applicable (“Permiso de obras preliminares”, DOM resolution). |
|  | Works Permit (“Permiso de edificación”, pesented, pending approval). Contractor shall be in charge at it´s sole cost of the hydrogeological report (and shall be responsible of its approval) requested by the Municipal Works Department to rule out risks due to the presence of groundwater. |
| Interconnection | See Annex 05 |

  - Project specific permits

| Category | Permit |
| --- | --- |
| - | - |

- Contractor’s Permits (PAC Permits)

  - General Permits

| Category | Permit |
| --- | --- |
| Sectorial | Hazardous wastes storage (PAS 140, resolution from SEREMI de Salud) |
|  | Non-hazardous wastes storage (PAS 142, resolution from SEREMI de Salud) |
|  | Sanitary Report (“Informe sanitario”, resolution from SEREMI de Salud) (if applicable) |
|  | PAS 138, drinking water / sewage permit |
|  | PAS 146 Contractor shall proceed with the capture foreseen under PAS 146 prior to 15 February 2023 and must communicate it to the SAG 10 days in advance |
|  | Access Permit if required |
| Mining Rights | Mining Rights. Any issue arising for the lack of Mining Rights shall be the responsibily of the Contractor. |
| Building Permits | Building permit update, if applicable (“Modificación de permiso de edificación”, resolution from DOM) |
|  | Final Works Reception request (“Solicitud de recepción final de obra”, application for resolution from DOM) |
|  | Commercial Patent (“Patente Comercial”, from the Project’s Municipality) |
| Environmental | Contractor shall execute and comply, at it´s sole cost, with the RCA voluntary commitments: - Work force of 10% from the commune. - Communication with the community. - Installation of chiropteran houses. - Archaeological Inspection. - Project to improve water availability at the property level for soil improvement purposes Contractor shall execute and comply, at it´s sole cost, with the RCA conditions: - Comply with the regulations and conditions established by the Superintendence of Electricity and Fuels of the Metropolitan Region regarding electric safety. - Comply with the regulations and conditions established by the SEREMI of Transport and Telecommunications of the Metropolitan Region regarding trucks circulation. - Comply with the provisions of the Seremi MINVU of the Metropolitan Region regarding the obtainment of the IFC and the need to attach a hydrogeological characterization report to the Building Permit application. - Comply with the provisions of the Regional Health Authority of the Metropolitan Region regarding noise. - Comply with the provisions of the SEREMI of Public Works of the Metropolitan Region regarding the need of an access permit granted before the initiation of works. - Comply with the requirements of the DGA of the Metropolitan Region, especially in the case of water upwelling and underground water protection measures. - Update of the Voluntary Commitment “Project to improve water availability at the property level for soil improvement purposes” while processing PAS 160 and report to the SMA once obtained. |
| Interconnection | F21 form (from Distribution Company) |
|  | F22 form (from Distribution Company), which will not be necessary for its final obtaining. |
|  | Start Up Authorization for (“Autorizacion de puesta en servicio”, resolution from CEN) |
|  | Certificate for entry in operation (“Autorizacion de entrada en operacion comercial”, resolution from CEN) |
|  | Sign of the Interconeccion Agreement as a condition for PAC. |
|  | Electrical Declaration TE1 (“Declaracion electrica interior”, SEC) |

And any other Permit required for the performance or the Works which is not an Owner´s Permit.

  - Project specific permits

EPC Contractor should comply with and implement, as part of its Scope of Work, and included in the Contract Price at no additional cost, the following Project’s requirements:

- The Contractor shall make sure that the Provisional Acceptance takes place within the term defined in the Connection Gantt Chart delivered by the Project to the CNE at the moment of requesting the declaration of commencement of construction, as updated from time to time by the Contractor. Such update shall not (i) imply a change to the Guaranteed Commercial Operation Date nor the Guaranteed Provisional Acceptance Date; and (ii) trigger one or more of the events established by Article 72 of Supreme Decree No. 88.

Any Owner´s Permit that has not been obtained as of Signing Date shall be the responsibility of the Contractor.